{"text_format":"2","workbook":"xls","n_sheets":2,"sheets":["ACTIE LIJST","Contactgegevns"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":4,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"ACTIE LIJST","index":0,"n_rows":50,"n_cols":14,"rows_kept":50,"cut":false,"hidden":false,"merged":[[0,1,0,12],[2,7,2,12],[6,5,7,5]],"flags":["formulas_cached_only"]}
[null,"Logboek SGA Pacas"]
[]
[{"$nulls":7},"Status Overview"]
[null,"Review date:",null,null,"2023-07-04"]
[{"$nulls":6},"Current Date (reference)"]
[{"$nulls":6},"2023-07-06",{"$nulls":4},"Status","Count"]
[{"$nulls":11},"Ready",0]
[{"$nulls":11},"Late",0]
[{"$nulls":11},"Not yet due",8]
[null,"Nr.","datum issue","Overleg","Gebied","Actie","Opmerkingen/status","verantwoordelijk","Actie\nhouder","datum start","datum verwacht eind","datum \neind","Status","Kosten"]
[null,1,"2023-06-20","SGA","WTB","Druk lavafilters/Hydranten meten",null,"Jve/LS","LS","2023-06-13","2023-06-27",null,"ready"]
[null,2,"2023-06-21","SGA","E/PA","besturing verder uitwerken",null,"MJ","MJ","2023-06-21","2023-06-27","2023-06-21","ready"]
[null,3,"2023-06-20","SGA","WTB","uitzoeken drukval bij spoelen filter B&K",null,"BvD/LS","BvD","2023-06-13","2023-07-04","2023-06-27","ready"]
[null,4,"2023-06-20","SGA","Beheer/WTB","actielijst maken om installatie samen te laten draaien om zo drukval te voorkomen","10-7-2023 testen","Bvd/JvE","JvE","2023-06-20","2023-07-24",null,"ready"]
[null,5,"2023-06-13","SGA","E/PA + HVK","protocollen","TCD en handleidingen ontvangen van GMB 09-06-2023","MvH/TC","TC","2023-06-13",null,null,"not yet due"]
[null,6,"2023-06-20","SGA","C","beplating en afwerking roosters","Wopereis","MS","MS","2023-06-13",null,null,"not yet due"]
[null,7,"2023-06-13","SGA","C","Doseerpunten kranen","GMB","MS","MS","2023-06-13",null,null,"not yet due"]
[null,8,"2023-06-06","SGA","Beheer","Naar voren halen nieuwe bedrijfswater installatie en leiding werk","Renovatie project Oijen","JB/WvdH","JB","2023-06-06",null,null,"not yet due"]
[null,10,"2023-07-04","SGA","TBMA","lospunt slang detectie","zelfde als bij Pacas Dinther","FG","FG","2023-06-06",null,null,"not yet due"]
[null,11,"2023-07-04","SGA","C","Weg ophalen","GMB","MS","JM","2023-07-05","2023-07-19",null,"not yet due"]
[null,12,"2023-07-11","SGA","Beheer","TCD omzetten naar beheer","Brenda  en Bas ten Bulte, Ton B","BvdD",null,"2023-07-05",null,null,"not yet due"]
[null,13,"2023-06-27","SGA","TBMA","Filter op doseerunit in TCD?","Marcel gemeld","FG","FG","2023-07-04",null,null,"not yet due"]
[null,14,"2023-07-04","SGA","Beheer","Nieuwe bedrijfswater unit capaciteit toereikend","uit hoofd project","BvD","BVD","2023-07-04","2023-07-11",null,"ready"]
[null,15]
[null,16]
[null,17]
[null,18]
[null,19]
[null,20]
[null,21,{"$nulls":10},""]
[]
[null,20]
[null,21]
[]
[]
[null,18,{"$nulls":10},""]
[null,19,{"$nulls":10},""]
[null,20,{"$nulls":10},""]
[null,21,{"$nulls":10},""]
[null,22,{"$nulls":10},""]
[null,23,{"$nulls":10},""]
[null,24,{"$nulls":10},""]
[null,25,{"$nulls":10},""]
[null,26,{"$nulls":10},""]
[null,27,{"$nulls":10},""]
[null,28,{"$nulls":10},""]
[null,29,{"$nulls":10},""]
[null,30,{"$nulls":10},""]
[null,31,{"$nulls":10},""]
[null,32,{"$nulls":10},""]

{"sheet":"Contactgegevns","index":1,"n_rows":12,"n_cols":8,"rows_kept":12,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}
[]
[null,"Wie","IN.","Mobiel","Email","Rol","Vervanger","Opmerkingen"]
[]
[null,"Oane Stielstra","OS","06-10215319","ostielstra@aaenmaas.nl","Engineer WTB",null,"SGA teamlid"]
[null,"Miranda van Hees","MvH","06-13194236","mvanhees@aaenmaas.nl","Engineer E en PA",null,"Op afroep"]
[null,"Fred Hooijmaijers","FH","06-12119227","fhooijmaijers@aaenmaas.nl","Interne opdrachtgever"]
[null,"Marcel Damen","MD","06-53394198","mdaamen@aaenmaas.nl","Proces operator",null,"SGA teamlid"]
[null,"Roel Paulissen","RP","06-51197101","rpaulissen@aaenmaas.nl","Proces operator",null,"SGA teamlid"]
[null,"Mark Elders ","ME","06-12914894","melders@aaenmaas.nl","Bedrijfsleider RWZI"]
[null,"Bastiaan Hommel","BH","06-20530328","bhommel@aaenmaas.nl","Senior procestechnoloog",null,"SGA teamlid"]
[null,"Marga Heijmans","MH","06-20520638","mheijmans@Aaenmaas.nl","Procestechnoloog"]
[null,"Erik Andriessen","EA","06-22956539","eandriessen@aaenmaas.nl","Projectleider","OS","SGA teamlid"]